## 1. Overview
Section | Value | Unit
Implementation - Total hours | 2352 | h
Implementation - Total cost | 2020948.65 | CZK
Hardware Price | 1584727.2 | CZK
Non-Implementation Overhead Cost | 137000 | CZK
Annual Operating Costs | 778000 | CZK/yr
5-Year Total Price | 7632675.85 | CZK

## 2. Implementation
Category | Task | Assigned To | Hours | Cost (CZK) | Mandays
Design | Software Architecture (.NET MAUI) | Kristián, Michal | 80 | 68739.75 | 10 | 1 MD = 8h
Design | UI/UX Design | Jonáš, Aneta, Kristián | 120 | 103109.625 | 15
Design | Initial GUI Layout (Draft) | Štěpán, Ondřej | 80 | 68739.75 | 10
Design | Final Graphic Mockup | Štěpán, Ondřej | 40 | 34369.875 | 5
Implementation | 3D Library Selection & Integration | Kristián | 160 | 137479.5 | 20
Implementation | DB Analysis (SQLite/JSON) | Petr, Michal | 64 | 54991.8 | 8
Implementation | Data Model & ER Diagram | Petr, Michal | 64 | 54991.8 | 8
Implementation | DB Schema Implementation | Petr | 40 | 34369.875 | 5
Implementation | Data Seeding (Wheelchair Components) | Petr | 40 | 34369.875 | 5
Backend | Component Data Models | Michal | 88 | 75613.725 | 11
Backend | Compatibility Rule Engine | Michal | 40 | 34369.875 | 5
Backend | Clinical Recommendation Logic | Michal | 32 | 27495.9 | 4
Frontend | UI Components & Layout | Ondřej, Štěpán | 104 | 89361.675 | 13
Frontend | Configurator Selection Logic | Ondřej | 56 | 48117.825 | 7
Frontend | UI and 3D Engine Integration | Kristián, Štěpán | 104 | 89361.675 | 13
Frontend | Dynamic 3D Model Updates | Kristián, Štěpán | 24 | 20621.925 | 3
Testing | Logic Unit Tests | Michal | 32 | 27495.9 | 4
Testing | User Acceptance Testing (FZS) | Štěpán | 8 | 6873.975 | 1
TOTAL |  |  | 1176 | 1010474.325 | 147

## 3. Non-Implementation Tasks
Task | Assigned To | Hours | Mandays | Cost (CZK)
Project Initialization & Setup | Štěpán | 24 | 3 | 28900.8 | 1 MD = 8h
Requirements Analysis & Scope | Petr, Štěpán | 32 | 4 | 38534.4
Client Consultations (FZS, FDU) | Štěpán, Jonáš | 16 | 2 | 19267.2
SRS Documentation | Petr, Štěpán | 240 | 30 | 289008
Business Plan & WBS Creation | Petr | 128 | 16 | 154137.6
Client Confirmation & Protocol | Petr, Štěpán | 48 | 6 | 57801.6
Ongoing Project Management | Štěpán | 120 | 15 | 144504
CI/CD & DevOps Pipeline | Štěpán | 50 | 6.25 | 60210
TOTAL |  | 658 | 82.25 | 792363.6

## 4. HW Price
Component | Unit Price (CZK) | Qty | Total (CZK) | Source
Android Tablet 10" (ARM64, Vulkan 1.1) | 9500 | 5 | 47500 | alza.cz
Protective Case (Medical Grade) | 1200 | 5 | 6000 | czc.cz
Charging Hub / Station | 3500 | 2 | 7000 | i-tec.pro
Clinical Testing Stand | 4000 | 2 | 8000 | ergostand.cz
TOTAL |  |  | 68500

## 5. Staffing Resources
Role | Name | Gross Salary | Total Cost (+33.8%) | Hourly Cost | Margin (20%) | Billable Rate
Project Leader | Štěpán Bříza | 120000 | 160560 | 1003.5 | 200.7 | 1204.2
DB Master & QA | Petr Chrz | 80000 | 107040 | 669 | 133.8 | 802.8
Structural Engineer | Kristián Kameník | 95000 | 127110 | 794.4375 | 158.8875 | 953.325
Backend Developer | Michal Jonáš | 90000 | 120420 | 752.625 | 150.525 | 903.15
Frontend Developer | Ondřej Všelko | 90000 | 120420 | 752.625 | 150.525 | 903.15
UI/UX Designer | Jonáš Bahner | 70000 | 93660 | 585.375 | 117.075 | 702.45
3D Modeler | Aneta Smetanová | 70000 | 93660 | 585.375 | 117.075 | 702.45
3D Modeler | Kristián Knap | 70000 | 93660 | 585.375 | 117.075 | 702.45
AVERAGE RATE | [5 empty] | 859.2469

## 6. Yearly Payments
Cost Item | Annual Amount (CZK)
Cloud Hosting & Database Sync (Azure/AWS) | 45000
Maintenance & Tech Support (10h/month) | 144000
Legislative & MDR/GDPR Updates | 80000
Office Rent & Admin Overhead | 120000
TOTAL ANNUAL COST | 389000

## 7. Business Plan
Variable | Meaning | Value
$N$ | Number of configurations per year | 500
$T$ | Time saved per configuration (hours) | 2
$C_h$ | Therapist hourly rate (CZK/h) | 1500
$E$ | Share of eliminated errors | 15%
$C_e$ | Cost of fixing one manual error | 5000
V | Total Annual Social Value | 1875000
P | Annual License Fee (10% Value Capture) | 187500